## Sheet1
Category | Task | Who | Est. Time (hr) | Completed
Planning | Project Plan | Jakob | 2 | 2022-05-10
| Exploratory Questions | Alysia/Charlie | 1 | 2022-05-09
| Data Sources/Summary | Alysia/Charlie | 1 | 2022-05-06
| Infrastructure Diagram | Jakob | 2 | 2022-05-09
| Napkin Drawing: Visualizations | Charlie | 1
| Napkin Drawing: Dashboard | Charlie | 1 | 2022-05-10
| Napkin Drawings Feedback | Charlie | 1
| Data Sources ERD | Alysia | 3 | 2022-05-11
Kafka Setup | Create container | Charlie | 0.5 | 2022-05-09
| Create infrastructure within container: Producer, Consumer, Databrick | All | 1.5
| Set up Producer with APIs | Alysia/Charlie | 1 | 2022-05-12
| Set up Consumer to collect from Producer | Alysia/Charlie | 2 | 2022-05-12
| Set up Consumer to send data to ETL databrick | Charlie | 3
| Set up ETL databrick to send to ML databrick | Charlie/Jakob | 2
| Set up ML databrick to send to visualization databrick | Charlie/Jakob | 1
| Set up visualization databrick to send to Dashboard | Charlie/Jakob | 1
SQL Database | Create and set up SQL Database | Jakob | 0.5 | 2022-05-12
| Import data into database tables | Jakob | 2 | 2022-05-12
| Create normalized database | Jakob | 8
Data ETL | Import data into dataframes | Alysia | 3 | 2022-05-12
| Merge data | Alysia | 3
| Remove duplicates and nulls | Alysia | 4 | 2022-05-13
| Aggregate/group data | Alysia | 4 | 2022-05-13
| Export raw data to visualizations |  | 1
| Write ETL report | Jakob | 4
| Proofread ETL report | Charlie | 2
Machine Learning | Instantiate and train ML model(s) | Charlie | 2
| Adjust model hyperparameters | Charlie | 2
| Export ML data to visualizations | Charlie | 1
Visualizations | Extract data needed for each visualization | Jakob | 2
| Create visualizations | Jakob | 4
| Format visualizations | Jakob | 2
Dashboard | Implement visualizations | Jakob | 3
| Format and arrange visualizations | Jakob | 3
Project Technical Report | First draft | Alysia | 8
| Proofreading and Formatting | Jakob | 2
| Final Draft | Alysia | 2
Presentation Slides | First draft/text | Alysia | 3
| Proofreading | Charlie | 1.5
| Visualizations, images, formatting | Jakob | 1
Presentation Dry Run | Determine who presents on what | All | 0.5
| Independent practice | All | 1
| Group practice | All | 2
Github | Create shared repo and create initial readme | Charlie | 0.5
| Complete readme | Jakob | 1
| Organize Materials | Charlie | 2
| Submit Link | Charlie | 0.5
| Total planned hours |  | 99.5

## Rubric Requirements
Rubric:
Task Division | All tasks look to be evenly split among team members.
Exploratory Questions | Project plan accounts for Exploratory Questions.
Napkin Drawings & Feedback for Visualizations | Project plan accounts for napkin drawings of the visualizations and their feedback.
Napkin Drawings + Feedback for the Dashboard | Project plan accounts for napkin drawings of the dashboard and their feedback.
Repeatable ETL Report | Project plan accounts for the repeatable ETL report.
Dashboard | Project plan accounts for building a dashboard in Dash or report in Power BI with Python.
Project Technical Report | Project plan accounts for technical report summary.
Presentation Slides | Project plan accounts for presentation slides.
Presentation Dry Run | Project plan accounts for presentation dry run.
LMS:
Everything needed for Kafka
Writing the repeatable ETL report
Building the machine learning model
Refining the machine learning model for higher accuracy
Building a dashboard with Dash or Power BI with Python
Creating napkin drawings of visualizations
Creating napkin drawings of a dashboard
Getting feedback from at least 2 other classmates in other groups on the napkin drawings
Documenting the feedback
Writing the technical report
Writing the presentation
Coming up with a plan for presenting the presentation